## Sheet2
Date | Day | Hours worked | Tasks done | Comments
2022-08-27 | Saturday | 6 | Studied and researched requirement specification.
2022-08-28 | Sunday | 8 | Created Trello board for SWAP website. Added 'To Do', 'Doing' and 'Done' cards in Trello. Added 'Literature Review', 'Requirement Engineering', 'Designing', 'Testing and review' and 'Report' to 'To do' card in Trello. Added checklist for 'Literature Survey' card. Added checklist for 'Requirement engineering' card. 'Requirement Engineering' card was moved from 'To Do' to 'Doing'. Began to write functional requirements. | Works were started ahead before tracking tasks in Trello.
2022-08-29 | Monday | 8 | Literature Search' and 'Literature Review' checked as complete. Completed functional requirements. Supervisor meeting via Google meet.
2022-08-31 | Wednesday | 6 | Began to write non functional requirements.
2022-09-01 | Thurday | 6 | Completed non functional requirements. Consulted Supervisor via WhastApp.
2022-09-02 | Friday | 6 | Reviewed both functional and non functional requirements.
2022-09-03 | Saturday | 10 | Marked 'Questionnaire' as completed in Trello. Marked 'Survey' as completed in Trello. Marked ' Functional requirements' as completed in Trello. Marked 'Non Functional requirements' as completed in Trello. Checked 'Risk Assessment' as completed. Completed 'Wireframes(version 1)'. Add 'Resource Allocation' to 'To Do' card in Trello. Added 'Implementation' to 'To do' in Trello'. Supervisor meeting via Google meet.
2022-09-04 | Sunday | 8 | Created WBS. Added 'Work Breakdown Structure' to Trello and WBS chart was attached. Added 'Time estimation' card to Trello. Gantt chart was completed and attached. Completed Hardware and Software requirements. Completed activity diagram.
2022-09-05 | Monday | 8 | First milestone was completed (AE1)
2022-09-06 | Tuesday | 6 | Began 'Requirement Analysis and negotiation'. Did a study on requirement analysis and negotiation.
2022-09-07 | Wednesday | 6 | Gathered requirements were analyzed.
2022-09-08 | Thursday | 6 | Completed Requirement prioritization.
2022-09-09 | Friday | 6 | Set of problematic requirements were identified, which were negotiated.
2022-09-12 | Monday | 8 | Completed requirement negotiation and a compromised set of requirements were obtained.
2022-09-13 | Tuesday | 10 | Began requirement verification and validation. Conducted a study on requirement verification/ validation. Research on UI concepts and color matching theory.
2022-09-14 | Wednesday | 6 | Began requirement verification/validation.
2022-09-15 | Thurday | 6 | Designed interfaces of the system.
2022-09-16 | Friday | 6 | Designed interfaces of the system.
2022-09-19 | Monday | 6 | Designed interfaces of the system.
2022-09-20 | Tuesday | 6 | Designed interfaces of the system.
2022-09-21 | Wednesday | 5 | Completed requirement verification/validation
2022-09-22 | Thurdsday | 6 | Began Designing and implementation.
2022-09-23 | Friday | 0 | None
2022-09-24 | Saturday | 0 | None
2022-09-25 | Sunday | 0 | None
2022-09-26 | Monday | 0 | None
2022-09-27 | Tuesday | 0 | None
2022-09-28 | Wednesday | 0 | None
2022-09-29 | Thursday | 0 | None
2022-09-30 | Friday | 0 | None
2022-10-01 | Saturday | 12 | Planning of Logo for the website Sketching of the logo Study on how to use "Adobe Illustrator" to design modern logos. Desiging of logo
2022-10-02 | Sunday | 0 | None
2022-10-03 | Monday | 0 | None
2022-10-04 | Tuesday | 0 | None
2022-10-05 | Wednesday | 8 | Created first version of logo. (version 1) Updated supervisor on project progress.
2022-10-06 | Thursday | 5 | Revised wireframes for changes.
2022-10-07 | Friday | 0 | None
2022-10-08 | Saturday | 3 | Further research on logo designing.
2022-10-09 | Sunday | 0 | None
2022-10-10 | Monday | 0 | None
2022-10-11 | Tuesday | 10 | Modifying wireframes (version 2). Created second version of logo. (version 2) Further study on UI elements.
2022-10-12 | Wednesday | 8 | Designing Er diagram Designing of relational schema Modified second version of logo. (version 2.1)
2022-10-13 | Thursday | 3 | Consulted supervisor to clarify doubts.
2022-10-14 | Friday | 0 | None
2022-10-15 | Saturday | 0 | None
2022-10-16 | Sunday | 6 | Started creating a banner image for the website in Adobe Illustrator.
2022-10-17 | Monday | 5 | Modifed banner image.
2022-10-18 | Tuesday | 0 | None
2022-10-19 | Wednesday | 8 | Created the logo for the website and finalized it. (version 3) "Swap website" folder was created to add all the files related to project.
2022-10-20 | Thursday | 5 | Working on wireframes Reviewed feasibility study survey Updated Trello Reviewed Gantt chart "Index.html" page was created. Initial commit to Github. Comitted 'Index.html' page.
2022-10-21 | Friday | 4 | Completed an illustration images for banner image for the website.
2022-10-22 | Saturday | 0 | None
2022-10-23 | Sunday | 10 | "css" folder was created to add additional css files. "Diagrams" folder was created to add project related diagrams. "images" folder was created to add all the images that needs to be included in the website. "js" folder was created to add JavaScript files. Completed home page wireframe. 2nd commit to Github. "index.html" page was modified, added css and JavaScript links. 3rd commit to Github. Added activity diagrams to Github. 4th commit to Githib. Re-added modified activity diagrams. 5th commit to Github. Renamed activity diagrams. 6th commit to Github. Added 'Home' page wireframe. 7th commit to Github. Modified "home.html", added Google fonts link, menu bar, banner and description. Modified "style.css" . Added logo and banner images.
2022-10-24 | Monday | 2 | Updated supervisor on project progress.
2022-10-25 | Tuesday
2022-10-26 | Wednesday | 5 | 8th commit to github. Modified "index.html" , minor modifications Modified "style.css" file. Added sample log file.
2022-10-27 | Thursday | 3 | Study on sweet alert and its usage.
2022-10-28 | Friday | 0 | None
2022-10-29 | Saturday | 0 | None
2022-10-30 | Sunday | 0 | None
2022-10-31 | Monday | 0 | None
2022-11-01 | Tuesday | 0 | None
2022-11-02 | Wednesday | 0 | None
2022-11-03 | Thursday | 8 | "dist" folder was created to add jquery files. "footer.php" page was created. "styles.php" page was created, used to include all the links related to CSS, JavaScript, fontawesome, Google fonts and sweet modals.
2022-11-04 | Friday | 10 | "books.php" page was created. "contact-us.php" page was created. "electronics.php" page was created. "login.php" was created. "product-details.php" page was created. "sign-up.php" page was created. 9th commit to Github. Added "styles.php" page, was created to added all the external links such as CSS, JavaScript, Google fonts, fontawesome and sweet alert. Initially created "styles.css" page was deleted and added "style.css" page. Modified "style.css" page. Added additional JavaScript files to "js" folder. Renamed "index.html" page as "index.php" and modified it, added tabs. Added necessary images. "header.php" page was created, includes menu bar and added to Github. "footer.php" page was modified, includes quick links and socials and added to Github. Jquery files were added to "dist" folder. Additional css files were added to "css" folder.
2022-11-05 | Saturday | 0 | None
2022-11-06 | Sunday | 0 | None
2022-11-07 | Monday | 0 | None
2022-11-08 | Tuesday | 0 | None
2022-11-09 | Wednesday | 0 | None
2022-11-10 | Thursday | 0 | None
2022-11-11 | Friday | 8 | 10th commit to Github. Modified "style.css". Modified "index.php", made minor changes. Modified "header.php", proper links were added in the menu bar. Modified "footer.php", proper links were added to anchor tags. Added "sign-up.php", "product-details.php", "login.php", "furnitures.php", "electronics.php", "contact-us.php", "books.php" and "add-product.php" pages to Github. Added 2 images to images folder.
2022-11-12 | Saturday | 5 | 11th commit to Github. Modified and added "home" wireframe. Added "furnitures", "electronics" and "books" pages wireframes.
2022-11-13 | Sunday | 5 | Study on privacy policy for website.
2022-11-14 | Monday | 5 | Study on terms and conditions for website.
2022-11-15 | Tuesday | 0 | None
2022-11-16 | Wednesday | 0 | None
2022-11-17 | Thursday | 4 | "code_lib.inc" page was created. "db_connection.php" page was created.
2022-11-18 | Friday | 4 | "furnitures.php" page was created. "header.php" page was deleted and re-created. "style.css" page was created.
2022-11-19 | Saturday | 2 | "user-account.php" page was created.
2022-11-20 | Sunday | 0 | None
2022-11-21 | Monday | 4 | "add-product1.php" page was created. "edit-product.php" page was created.
2022-11-22 | Tuesday | 3 | "sign-up2.php" page was created. Supervisor meeting physically.
2022-11-23 | Wednesday | 4 | "login2.php" page was created. "logout.php" page was created. "validate-user.php" page was created.
2022-11-24 | Thursday | 3 | Supervisor meeting physically.
2022-11-25 | Friday | 6 | "about-us.php" page was created. "footer2.php" page was created. "header2.php" page was created. "help-and-support.php" page was created. "invalid-login.php" page was created. "privacy-policy.php" page was created. "terms-conditions.php" page was created.
2022-11-26 | Saturday | 10 | 12th commit to Github. Added "validate-user.php", "user-account.php", "terms-conditions", sign-up3.php", "sign-up2.php", privacy-policy.php", "logout.php", "login2.php", "invalid-login.php", "help-and-support.php", "header2.php", "footer2.php", "edit-product.php", "db_connection.php", "code_lib.inc.php", "add-productTest.php", "add-product3.php", "add-product2.php", "add-product1.php" and "about-us.php" pages. Added images to images, large and thumb folders. Modified "style.css". Modified "sign-up.php", made minor changes. Modified "product-details.php", included new code. Modified "login.php", minor changes were made. Modified "index.php", some parts of code were delted and new code were included. Modified "header.php", minor changes were made. Modified "furnitures.php", as footer and header would change based on login. Modified "footer.php", minor strucutral changes were made. Modified "electronics.php", as footer and header would change based on login. Modified "contact-us.php", as footer and header would change based on login. Modified "books.php", as footer and header would change based on login. Deleted "add-product.php" page.
2022-11-27 | Sunday | 8 | "edit-user-account.php" page was created. 13th commit to Github. Modified "user-account.php", minor changes were made. Modifed "sign-up3.php", minor changes were made. Modified "sign-up2.php", minor changes were made. Modified "login.php", included alert messages for invalid login. Modified "header2.php", minor changes were made. Modified "add-product2.php", made minor changes to SQL code. Modified "add-product1.php", made minor changes. Modified log files. Added "edit-user-account.php" page to Github. Completed "Edit user account" feature.
2022-11-28 | Monday | 8 | "add-product2.php" page was created. "confirm-post.php" page was created. 14th commit to Github. Modified "sign-up2.php", made minor changes for header location. Modified "sign-up.php", included alert messages. Modified "add-product2.php", made major changes to the code. Modified "add-product1.php", made minor changes. Deleted "sign-up3.php", "add-producttest.php" and "add-product3.php".
2022-11-29 | Tuesday | 8 | "dashboard.php" page was created. 15th commit to Github. Modified "style.css". Modified " header2.php", made minor changes. Modified "header.php", made minor changes. Modified "electronics.php", made minor changes. Modified "add-product2.php", SQL code was edited. Modified "add-product1.php", code was added to fetch data from the database. Added "dashboard.php" and "confirm-post.php" pages to Github.
2022-11-30 | Wednesday | 8 | "admin-login.php" page was created. 16th commit to Github. Added "test1.php", "test2.php" and "admin-login.php" pages to Github. Modified "style.css", "confirm-post.php", "add-product2.php" and "add-product1.php" pages. 17th commit to Github. Modified "style.css". Modified "confirm-post.php", code was added to fetch data from database.
2022-12-01 | Thursday | 3 | "admin-delete-post.php" page was created. "confirm-post2.php" page was created.
2022-12-02 | Friday | 12 | 18th commit to Github. Modified "user-account.php", added code to show posts added by user. Modified "style.css". Modified "confirm-post.php", added code to fetch data from database and show alert messages. Modified "add-product2.php", change SQL code. Modified "add-product1.php", added code to added post confirmation. Added "confirm-post2.php" and "admin-delete-post.php" pages to Github. 19th commit to Github. Modified "user-account.php". Modified "style.php". Modifed "confirm-post2.php", added code to show alert messags. Modified "confirm-post.php", made minor changes. Added "sample.php" file, to test user account page. 20th commit to Github. Modified "style.css". Modified "furnitures.php", added SQL code to fetch data from the database. Modified "electronics.php", added SQL code to fetch data from the database. Modified "books.php", added SQL code to fetch data from the database. Modified "admin-delete-post.php", added sessions and header locations. 21st commit to Github. Modified "furnitures.php",added code to limit fetching number of records from database and for pagination. Modified "electronics.php", added code to limit fetching number of records from database and for pagination. Modified "books.php", added code to limit fetching number of records from database and for pagination. 22nd commit to Github. Modified "styles.php", added additoinal bootstrap and Jquery files. Modified " style.css". Modified "furnitures.php", removed dynamic carousel and added code fetch data from database. Modified "electronics.php", removed dynamic carousel and added code fetch data from database. Modified "books.php", removed dynamic carousel and added code fetch data from database. Modified "add-product1.php", added code to preview images in add product page.
2022-12-03 | Saturday | 3 | "ajaxfile.php" page was created. 23rd commit to Github. Modified "user-account.php", added modal to edit product details, change user password and JavaScript to edit product using ajax. Modified "style.css". Modified "electronics.php", made minor changes. Modified "edit-user-account.php", made minor changes. Modified "edit-product.php", removed html code and only added php code. Modified "confirm-post2.php", "confirm-post.php" and "add-product1.php". Added "change-password.php" and "ajaxfile.php" to Github.
2022-12-04 | Sunday | 8 | "admin-sign-up.php" page was created. "admin-sign-up2.php" page was created. "change-password.php" page was created. "dashboard-carousel.php" page was created. "dashboard-header.php" page was created. 24th commit to Github. Modified "style.css", "login.php", "dashboard.php", "confirm-post2.php", "confirm-post.php", "change-password.php", "admin-login.php" and "admin-delete-post.php". Added "validate-admin.php", "dashboard-header.php", "dashboard-carousel.php", "admin-sign-up2.php", "admin-sign-up.php", "admin-logout.php" and "admin-login2.php". Deleted "test2.php", "test1.php" and "sample.php".
2022-12-05 | Monday | 8 | "admin-login2.php" page was created. "admin-logout.php" page was created. "validate-admin.php" page was created. 25th commit to Github. Modified "style.css", "furnitures.php", "electronics.php", "dashboard.php", "confirm-post2.php", "confirm-post.php", "books.php" and "admin-delete-post.php".
2022-12-06 | Tuesday | 0 | None
2022-12-07 | Wednesday | 8 | "customers.php" page was created. 26th commit to Github. Modified "user-account.php", "style.css", "index.php", "furnitures.php", "electronics.php", "edit-user-account.php", "dashboard.php", "dashboard-header.php", "confirm-post.php", "change-password.php", "boooks.php" and "ajaxfile.php". Added "user-account1.php" and "customers.php" files to Github.
2022-12-08 | Thursday |  | 27th commit to Github. Modified "style.css", "index.php", "electronics.php", "contact-us.php" and "about-us.php". Deleted "user-account1.php" file. 28th commit to Github. Modified "style.css" and "about-us.php" files.
2022-12-09 | Friday | 4 | AE2 report' folder was created. 29th commit to Github. Added project report to Github.
2022-12-10 | Saturday | 8 | 30th commit to Github. Modified "terms-conditions.php", "style.css", "privacy-policy.php", "help-and-support.php", "edit-product.php", "ajaxfile.php" and "add-product1.php".
2022-12-11 | Sunday | 8 | "admin.php" page was created. "ajaxfile1.php" page was created. "change-admin-password.php" page was created. "edit-admin-account.php" page was created.
2022-12-12 | Monday | 10 | "user-delete-post.php" page was created. 31st commit to Github. Modified "user-account.php", "styles.php", "style.css", "furnitures.php", "electronics.php","dashboard.php", "dashboard-header.php", "books.php" and "ajaxfile.php". Added "user-delete-post.php", "edit-admin-account.php", "change-admin-password.php" and "ajaxfile1.php". 32nd commit to Github. Added modified wireframes to Github. 33rd commit to Github. Login and sign up wireframes were added to Github. 34th commit to Github. Add product and profiloe wireframes were added to Github. 35th commit was added to Github. Edit product and view account details wireframes were added to Github. 36th commit to Github. Added change passowrd and help & support wireframes to Github. Modified "help-and-support.php" and "privacy-policy.php" files. 37th commit to Github. Modified "about-us.php" files and project report. Added privacy policy and terms & conditions wireframes to Github. 38th commit to Github. Added about us and my account wireframes to Github.
2022-12-13 | Tuesday | 6 | 39th commit to Github. Added admin login and dashboard wireframes to Github. 40th commit to Github. Modified "admin.php" file. Added confirm post and dashboard menus wireframes Github. 41st commit to Github. Added admin sign up and settings wireframes to Github. 42nd commit to Github. Added customers and edit admin account wireframes to Github. 43rd commit to Github. Modified porject report. Added admin change password and edit user account wireframes to Github. 44th commit to Github. Modified porject report, literature review was updated. 45th commit to Github. Modified porject report, completed literature review and all the completed wireframes were added to the report.
2022-12-14 | Wednesday |  | 46th commit to Github. Modified project report, started methodology topic. 47th commit to Github. Modified project report, included requirement/ specification topic to the report.
2022-12-15 | Thursday | 8 | 48th commit to Github. Modified project report, included requirement engineering topic. 49th commit to Github. Modified "style.css", "help-and-support", "footer2.php", "footer.php" and project report. 50th commit to Github. Modified project report, completed functional requirements topic. 51st commit to Github. Modified project report, completed requirement engineering project.
2022-12-16 | Friday | 10 | 52nd commit to Github. Modified "user-delete-post.php" and project report. Included test plan to the report. Fixed the error when user tries to delete a post. 53rd commit to Github. Modified "admin-sign-up.php" file, added JavaScript validation to the sign up form. 54th commit to Github. Modified "user-account.php", "styles.php", "sign-up.php", "admin.php" and "admin-sign-up.php" files. All forms were validated using JavaScript validation and sweet alerts were used to show error messages. 55th commit to Github. Modified "user-account.php", "sign-up2.php", "admin.php", "admin-sign-up2.php", "admin-sign-up.php" and project report.
2022-12-17 | Saturday | 8 | Deployed SWAP website in "000webhost" hosting platform.
2022-12-18 | Sunday | 8 | "admin-delete-account.php" page was created. "delete-account.php" page was created. 56th commit to Github. Added "delete-account.php" files to Github. Modified "user-account.php" and "db_connection.php" files. 57th commit to Github. Added "admin-delete-account.php" file. Modified "admin.php" file.
2022-12-19 | Monday | 3 | Strat test review.
2022-12-20 | Tuesday | 5 | Test review in progress.
2022-12-21 | Wednesday | 3 | Completed Test review
2022-12-22 | Thursday | 8 | 58th commit to Github. Modified "style.css", "confirm-post.php" and "add-product1.php".
2022-12-23 | Friday | 0 | None
2022-12-24 | Saturday | 8 | 59th commit to Github. Modified project report. 60th commit to Github. Added test cases. Elaborated test cases were added to Excel spreadsheet with more details.
2022-12-25 | Sunday | 6 | 61st commit to Github. Modified project report and completed the test cases.
2022-12-26 | Monday | 6 | 62nd commit to Github. Modified project report.
2022-12-27 | Tuesday | 3 | Modified project report.
2022-12-28 | Wednesday | 6 | 63rd commit to Github. Modified project report.
2022-12-29 | Thursday | 5 | Modified project report.
2022-12-30 | Friday | 6 | 64th commit to Github. Modified project report.
2022-12-31 | Saturday | 3 | Modified project report.
2023-01-01 | Sunday | 5 | 65th commit to Github. Modified project report. Supervisor meeting physically.
2023-01-02 | Monday | 5 | 66th commit to Github. Modified project report.
2023-01-03 | Tuesday | 5 | 67th commit to Github. Modified project report.
2023-01-04 | Wednesday | 5 | 68th commit to Github. Modified project report.
2023-01-05 | Thursday | 5 | Modified project report.
2023-01-06 | Friday | 8 | 69th commit to Github. Modified project report
2023-01-07 | Saturday | 8 | Modified project report. Consulted supervisor regarding poster presentation.
2023-01-08 | Sunday | 8 | 70th commit to Github. Made minor changes on web pages. Modified project report. Completed poster presentation poster
2023-01-09 | Monday | 5 | Completed Poster presentation video
Total work hours |  | 587 hours
Project library maintained were Github and Trello
|  | Github link | https://github.com/Sajidha377/Swap.git
|  | Trello link | https://trello.com/invite/project88390085/ATTI35f178a3c047ab7e43d508a427bac79dFC05BF9D